PLANNING PERFORMANCE FRAMEWORK

	ANNUAL REPORT 2011-2012
COMHAIRLE NAN EILEAN SIAR


	[image: image1.jpg](&)






1.
National Headline Indicators (NHIs)
	Key outcomes
	2011-2012
	Q1 – 12/13

	Development Planning:

· age of local/strategic development plan(s) (full years)Requirement: less than 5 years
· Development Plan Scheme: on track? (Y/N)
	4 
yes
	1
yes

	Effective Land Supply and Delivery of Outputs

· effective housing land: years supply 

· effective housing land supply

· housing approvals

· effective employment land supply

· employment  land take-up

· effective commercial floor space supply

· commercial floor space delivered
	Yes 5 years
365
219
51,199 ha

0 ha

3,598 m2
0 m2
	

	Development Management

Project Planning
· percentage of applications subject to pre-application advice

· number of major applications subject to processing agreement or other project plan

· percentage planned timescales met

Decision-making

· application approval rate

· delegation rate
	NA
0
N/A
99%

96%
	

	Decision-making timescales

Average number of weeks to decision:
· major developments

· local developments (non-householder)

· householder developments
	90.6

11.5
8.2
	0
9.6
7.8

	Enforcement

· time since enforcement charter published / reviewed (months)  Requirement: review every 2 years
· number of breaches identified / resolved
	Published April 2010/ Reviewed March 2012
51/42
	9/10


The Outer Hebrides has a high percentage of its landmass under Environmental designation. This together with other ‘sensitive area’ designations has required that EIA screening be carried out for most micro-turbine applications which have increased year on year, adding considerably to non-fee earning workloads.
The Outer Hebrides has the second highest number of Marine Atlantic Salmon farms in Scotland and with marked expansion in the sector to satisfy global demand, planning applications in this sector has been high with some very challenging cases drawing on the resources of a small team

The post consent processing of large scale wind has also drawn heavily on resource during 2011/12.
Customer Survey information collated by the Planning Service - and from work carried out by Audit Scotland (The Planning Service was a case study area for the recent Audit Scotland Planning Modernisation Report) - indicate a very high customer satisfaction rating.
Furthermore, the geography of the Outer Hebrides often presents difficulties in terms of service delivery.

[image: image2.jpg]The Outer Hebrides

" Tarbert

Stornoway

b Lochboisdale

Barra

tn Castlebay

CnEs MSA Licence no. 1000229965





PLANNING PERFORMANCE FRAMEWORK

2. 
Defining and measuring a high-quality planning service
	Open for business


	The Comhairle’s Planning Service is based in the Development Department’s Development Services section, alongside other services such as Economic Development, Business Gateway, Environmental Health, Trading Standards and Building Standards.  
The Development Services’ mission “is committed to providing forward thinking, professional and effective planning, building standards and housing services to facilitate economic, environmental and social development of the Outer Hebrides”.
Business planning is carried out jointly within the Department and Heads of Service and the Director work to develop integrated approaches to service provision.
The service offers free and available pre-application advice and has actively promoted pre-application discussion in relation to house design including promotion of the service on a Gaelic TV programme and, launch and promotion of a new Outer Hebrides Housing Design Guide.
Planning Officers are available to speak to customers during working hours each week day.  Where a customer wishes to speak to a particular officer they telephone the dedicated Planning number or the Comhairle’s customer service team to make an appointment.

The service organises multi-agency/special pre-application meeting where appropriate and has recently co-ordinated stakeholder meetings to aid post-consent variations and discharge of conditions process. It also hosted round table Key Agency events during preparation of the Local Development Plan.

The Comhairle’s Planning Service chaired the National Taskforce for aquaculture planning for two years and has led joint working in aquaculture planning across relevant local authorities.

In January 2012, the Scottish Government established four Enterprise Areas (EAs) in Scotland – including the Arnish Industrial Area as one of a group with a particular focus on low carbon manufacturing opportunities.  A specific protocol and single point of contact for handling development proposals for the Arnish Enterprise Area is now in place
The Comhairle’s Planning Service along with the Stornoway Trust, the Stornoway Port Authority, Stornoway Amenity Trust, Stornoway Historical Society, Lews Castle College UHI, Lews Castle Trust and HIE, has led an action programme for the Regeneration of the main centre of Stornoway.


	High quality development on the ground


	The Comhairle’s Local Development Plan promotes a new approach to design standards in the Outer Hebrides.  For the first time the Comhairle has held design awards for new house build – working jointly with the Scottish Government to deliver.  Our work has featured in a recent Government publication – Rural Design – Future Landscapes, and the winner featured on the Scottish Government website – inspirational designs.
The Planning Service input has influenced the design and implementation of a recent £70 million six school redevelopment programme throughout the Outer Hebrides contributing to the Outer Hebrides built environment through delivery of new, exciting and modern public buildings.
In addition, over the last 5 years the Planning Service has managed and implemented a successful Townscape Heritage Initiative within the heart of the Stornoway Conservation Area which has revitalising many buildings in Stornoway Town Centre.


	Certainty


	The Comhairle works with both internal and external consultees, monitoring their performance to ensure timely responses and has over the year sought dialogue and agreed interventions and changes to processes and approaches on both the part of the Service and the Consultees to address concerns.
The new LDP Development Strategy provides a clear indication for developers of where development will/will not be acceptable and the requirements for a high level of design quality.  Building on the experience of the current development plan, the Development Strategy is supported by policies and supplementary guidance that again provides definitive information on what is expected of developers in preparing and submitting applications and how decisions will be made.  It is anticipated that the LDP will be adopted in the near future within the timescale set out in the DPS.


	Communications, engagement and customer service


	The Comhairle has an up-to-date customer Charter for the Planning Service in place (2011).
The Planning Service has in place a customer survey available in paper and online formats and promoted at key stages in the planning process.

An annual stakeholder forum is held (over two locations) and stakeholders (including agents and developers) receive electronic updates on a quarterly basis.

The Comhairle hosts an annual meeting with the Aquaculture industry – in conjunction with the Scottish Salmon Producers Organisation (SSPO).

The Comhairle also follows corporate standards for handing of service complaints.

The Comhairle’s planning web site is keep up to date and the content measures well in recent government Pendleton scoring.


	Efficient and effective decision-making


	The Comhairle has an up to date scheme delegation to officers and clear arrangements for Committee Delegation also. The level of delegation is high (96%) and higher in comparison with previous years levels. The Comhairle, as of May 2012, has delegated decision making process to the Committee in order that decisions can be made without reference to the Full Comhairle where it can.  The Local Review Body meets as required – although the case load is very low.  
Planning application Case load is monitored by the Development Management Planning Manager and officers enabled to manage their caseload through issue of a weekly progress report to officers of their own caseload, arranged by development type and colour coded to highlight time taken/available against target – a traffic light system and monthly issue of cases determined again using traffic light system.
The Head of Service and the Planning Manager regularly review case loads to assess and respond to changes in the pattern of applications received by re-allocating duties within the team to meet delivery of priority developments and larger/more complex cases.


	Effective management structures


	The Planning Service is led by a Head of Service and delivered by two business units: Development Management and Strategic Planning and Projects – each business unit is headed by a Planning Manager.  The Head of Service and Planning Managers work collaboratively and across teams to deliver on service priorities.
Planning Service teams hold monthly meeting to review progress and Performance in monitored also at quarterly Departmental management meeting.  At every Comhairle Committee series the Department Reports on performance.
Planning Officer posts are generally career grade posts.  This encourages officers to progress up the career grade scale until they have obtained professional membership of the RTPI.  This helps with succession planning in that there are potentially fully qualified staff who would be eligible to apply for a management post if it became available.

See attached Departmental management structure.


	Financial management and local governance


	Budget setting is on annually basis and team budgets are monitored on a monthly basis.
The Planning Service finances are monitored on a monthly basis by the service managers.  If income or expenditure deviate significantly from the budgeted amount this is reported on.  Planning fee income is recorded in the case management System.  The service manager is able to query the database via a standard set of reports to enable an ongoing monitoring of income.

Corporate procurement policies ensure value for money.
To enable the Comhairle to monitor and report its performance it has adopted ‘Interplan’ by CAM management solutions, as it’s electronic performance management system.  Since August 2009, when the system went live, Interplan has been used to track the progress of the Comhairle service business plans and to report on progress made.  Because it provides a real time integrated business planning and performance monitoring system within the Comhairle it facilitates more frequent and flexible reporting and a commitment has been made to provide quarterly reporting of business plans and performance.



	Culture of continuous improvement


	The Development Department promotes an ethos of openness and continuous improvement.  During 2011, Investor in People ‘bronze’ status was retained through a highly satisfactory mid -term review.  The Departments Staff Forum also continues to develop ways in which staff can be fully involved in developing the business of the Department.
Opportunities to develop existing staff is sought and acted upon when they present themselves - enabled through the Comhairle’s SDA process.
Staff input to business planning exercises through regular events and are encouraged to bring forward ideas for service improvement.
Provision of training from other agencies (e.g. SEPA).
Involvement in DP and DM forums for the sharing and exchange of information and good practice with others..
The Head of Service meets collectively with other Heads of Planning in the Highlands and Islands to benchmark and learn from good practice across a range of topic areas.




3.
Supporting evidence
Part 2 of this report was compiled, drawing on evidence from the following sources.

· Development Plan Scheme 2012

· Development Department Business Plan Report 2011/12
· Development Department Business Plan 2012/13

· Development Department Management Structure 2012
· Planning Service Charter 2011
· Stornoway Regeneration Action Plan 2012
· Arnish Enterprise Area Planning protocol 2012
· Planning Service Customer survey
· Delivering Planning Reform for Aquaculture 1 & 2

4.
Service improvements: 2012-13

In the coming year we will:

· Review our web site to deliver a more customer focused product
· Develop use of the Uniform case management system in the service
· Promote the new permitted development rights
· Implement a one year action plan to assist public understanding/awareness of the planning system
· Implement a design awareness programme for the year
· Adopt the Comhairle’s Local Development Plan and associated Supplementary Guidance
· Adopt the LDP Action Programme

· Implement a review of planning conditions
Delivery of our service improvement actions in 2011-12:

	Committed improvements and actions
	Complete?

	Implementation of CRM for front desk service at main council office
· Successful implementation and operation of a corporate Customer Relation Management (CRM) system to deal with all planning ‘footfall’ and removal of planning service desk at main council offices, Stornoway.

	Yes

	Promotion of electronic submission 
· A six point action plan delivered to promote e-planning
· Evidence of gradual increase in e-application numbers

	Yes

	Review Policies and Procedures in Development Management
· Updated and approved a new Scheme of Delegation
· New policy agree on non-material variations to planning consents

· Implemented findings of an internal audit report for the DM service
· Improved processes for EIA developments implemented

· Implemented new Idox software for Public Access for Planning


	Yes

	Prepare advice note on small scale wind turbines
· Guidance note prepared and agree by the Comhairle
· Published the Guidance Note.

	Yes

	Implement a design awareness programme
· Revised Development Plan Design Policy drafted and consulted on.
· Design related web content updated and integrated.

· Featured on Scottish Government  inspiration designs website

· Stakeholders kept up-to-date through quarterly updates.
· ‘Kit house redesign project’ available through Scot. Govt. website.
· Planning staff design negotiation training delivered.
· Design Awards scheme developed and comprehensively launched. Awards panel appointed and design award ceremony hosted.

	Yes

	Consult on LDP and Supplementary Guidance
· LDP Proposed Plan consultation held September – November 2011.
· Consultation on 5 supplementary guidance held in parallel with LDP consultation.
· Proposed LPD submitted to Scottish Ministers for examination April 2012.
· 4 Supplementary Guidance approved by Comhairle.
· Further consultation on revised Wind Energy SG commenced September 2012.
	Yes


Appendix I
PLANNING PERFORMANCE FRAMEWORK

OFFICIAL STATISTICS
Decision-making timescales

	
	
	Average timescale (weeks)

	Category
	Total number of decisions 2011-2012
	2011-2012
	2012-2013

Q1

	Major developments
	2
	90.6
	-

	Local developments (non-householder)

· Local: less than 2 months

· Local: more than 2 months
	195 (60.9%)

125 (39.1%)
	7.1

18.3

	7.1

16.8

	Householder developments

· Local: less than 2 months

· Local: more than 2 months
	79 (84%)

15 (16%)
	6.9

14.8
	6.7

13.4



	Housing developments

Major

Local housing developments

· Local: less than 2 months

· Local: more than 2 months
	-

83 (65.9%)

43 (34.1%)
	-

7.4

14.8
	-

7.5

12.6

	Business and industry

Major

Local business and industry

· Local: less than 2 months

· Local: more than 2 months
	-

21 (63.6%)

12 (36.4%)
	-

7.3

18.5
	-

7.8

17.8

	EIA developments
	6
	34
	174.7

	Other consents*
	94
	8.8
	5.7

	Planning/legal agreements**
	1
	158.9
	195.5

	Local reviews
	0
	0
	0


* Consents and certificates: Listed buildings and Conservation area consents, Control of Advertisement consents, Hazardous Substances consents, Established Use Certificates, certificates of lawfulness of existing use or development, notification on overhead electricity lines, notifications and directions under GPDO Parts 6 & & relating to agricultural and forestry development and applications for prior approval by Coal Authority or licensed operator under classes 60 & 62 of the GPDO. 
** Legal obligations associated with a planning permission; concluded under section 75 of the Town and Country Planning (Scotland) Act 1997 or section 69 of the Local Government (Scotland) Act 1973
Decision-making: local reviews and appeals
	
	
	Original decision upheld

	Type
	Total number of decisions
	2011-2012

No.          %
	2012-2013

No.          %

	Local reviews
	
	-
	-
	-
	-

	Appeals to Scottish Ministers
	
	1
	0.0%
	-
	-


Enforcement activity
	
	2011-2012
	2012-2013

	Cases taken up
	10
	3

	Breaches identified
	51
	9

	Cases resolved
	42
	10

	Notices served***
	6
	2

	Reports to Procurator Fiscal
	0
	0

	Prosecutions
	0
	0


***
Enforcement notices; breach of condition notices; planning contravention notices; stop notices; temporary stop notices; fixed penalty notices, and Section 33 notices.
Context
The Outer Hebrides has an exceptionally high percentage of its landmass under Environmental designation with the South Lewis, Harris and North Uist National Scenic Area and the South Uist Machair National Scenic area covering approximately 50% of its landmass.  This together with other ‘sensitive area’ designations, (many of which cover inhabitated areas), has required that EIA screening be carried out for most micro-turbine applications which have increased year on year, adding considerably to non-fee earning workloads. 

The Outer Hebrides has the second highest number of Marine Atlantic Salmon farms in Scotland and with marked expansion in the sector to satisfy global demand; planning applications in this sector has been high with some very challenging cases drawing on the resources of a small team
The post consent processing of large scale wind has also drawn heavily on resource during 2011/12 and continues to do so into Q1.  

Appendix II
WORKFORCE AND FINANCIAL INFORMATION
Organisational Charts

[image: image3.emf]Malcolm Burr

Chief Executive

Calum Maciver

Director of Development 

Department

Iain Mackinnon

Director of Technical 

Services

Iain Macaulay

Director of Social and 

Community Services

Joan Mackinnon

Director of Education

Robert Emmot

Director of Finance

Keith Bray

Head of Development 

Services

John Gillies

Building Standards 

Manager

Morag Ferguson

Planning Manager

(Development 

Management)

Iain Watson

Housing Services Manager

Diane Macpherson

Planning Manager

(Policy)

Comhairle Nan Eilean Siar

Organisational Chart



[image: image4.emf]Housing 

Services

Manager

Iain Watson

Service Team

Leaders

Director

Calum Iain MacIver

Development Department Structure June  2012 

Head of Development 

Services

Keith Bray

Building Standards 

Officer  (Career Grade) 

(Balivanich)

John Macmillan

Planning 

Manager 

(Development 

Management)

Morag Ferguson

Research Officer

Kathleen Shirkie

Biodiversity Officer

(Balivanich)

Anne Maclellan  (17.5  Hrs)

Planning Officer

(Career Grade)

Isla MacArthur

Planning Officer

(Career Grade)

Mairi Maciver

Strategic Planning  & 

Projects

Building Standards 

Officer  (Career Grade)

George Stewart

Building Standards 

Officer  (Career Grade) 

Alasdair Maclean

Building Standards 

Officer  (Career Grade)

Ian MacRitchie

Building Standards 

Officer  (Career Grade) 

(Balivanich)

Elizabeth Spark

Technical Support Officer

Caitrina MacFarlane

Senior

Building Standards 

Officer

Donald Thomson

Building Standards 

Assistant 

Mark Macleod

Planning Officer

(Balivanich)

Hannah Morrison

Planning Officer

(Balivanich)

Robert Patrick

Planning Support Officer

Anne Mackenzie

Planning Officer

Cathy Leary

Planning Officer 

Helen Maclennan

Homeless Services 

Manager

Lorraine Graham

Private Sector Housing 

Manager

Andrew White

Housing Strategy  & 

Development Officer

Isobel MacKenzie

Admin Assistant

Murdina MacKenzie

Housing Strategy 

Assistant

Kathleen Harper

Homeless Persons Asst

Margaret MacPhail

Homeless Support 

Officer

Edna Morrison

Accommodation Warden

Heather Murray

Accommodation Warden

Finlay MacSween

Accommodation Warden

Grant Hunter

Clerk/Typist PT

Catriona Macdonald

Development 

Management

Housing Services Building Standards

Planning 

Manager  (Policy) 

(Balivanich)

Diane 

Macpherson

Building 

Standards 

Manager

John Gillies

Planning Technician

Kenny Maciver

Technician

Susan Rabe

THI Project Manager

Ian Wilson

Clerical Assistant

Marina Graham

Planning  Officer 

Eric Wojchik

Tenancy Support 

Worker (Balivanich)

Mary Steele

Service Team

Leaders

Planning Officer  (PT) 

Mairi Mackinnon

Planning Enforcement 

Officer 

Iain Macleod

Head of Economic 

Development

Joe Macphee

Consumer & Environmental 

Services Manager

Colm Fraser

Consumer & Environmental 

Services Team

Economic Development Team

Strategy Team

Strategy Manager

John Cunningham

Countryside Access and 

Environment Officer

Paul Tyler  (17.5 Hrs)

 


PAGE  
2

_1403947031.vsd
Team Title�

�

Company Name
￼�

�

�

Company Name
Department Name�

￼


Company Name


￼


Title


￼


Title


￼


Subtitle


Title


Title
￼


Title
￼


Title
￼


Company Name/Title
￼


Company Name/Title


￼


Title
￼


Title
￼


Subtitle


￼


Title


Malcolm Burr
Chief Executive


Calum Maciver
Director of Development Department�

Iain Mackinnon
Director of Technical Services�

Iain Macaulay
Director of Social and Community Services�

Joan Mackinnon
Director of Education�

Robert Emmot
Director of Finance�

Keith Bray
Head of Development Services�

John Gillies
Building Standards Manager�

Morag Ferguson
Planning Manager
(Development Management)�

Iain Watson
Housing Services Manager�

Diane Macpherson
Planning Manager
(Policy)�

Comhairle Nan Eilean Siar
Organisational Chart




_1410354541.doc


[image: image1.emf]Housing 


Services


Manager


Iain Watson


Service Team


Leaders


Director


Calum Iain MacIver


Development Department Structure June 2012 


Head of Development 


Services


Keith Bray


Building Standards 


Officer (Career Grade) 


(Balivanich)


John Macmillan


Planning 


Manager 


(Development 


Management)


Morag Ferguson


Research Officer


Kathleen Shirkie


Biodiversity Officer


(Balivanich)


Anne Maclellan (17.5 Hrs)


Planning Officer


(Career Grade)


Isla MacArthur


Planning Officer


(Career Grade)


Mairi Maciver


Strategic Planning & 


Projects


Building Standards 


Officer (Career Grade)


George Stewart


Building Standards 


Officer (Career Grade) 


Alasdair Maclean


Building Standards 


Officer (Career Grade)


Ian MacRitchie


Building Standards 


Officer (Career Grade) 


(Balivanich)


Elizabeth Spark


Technical Support Officer


Caitrina MacFarlane


Senior


Building Standards 


Officer


Donald Thomson


Building Standards 


Assistant 


Mark Macleod


Planning Officer


(Balivanich)


Hannah Morrison


Planning Officer


(Balivanich)


Robert Patrick


Planning Support Officer


Anne Mackenzie


Planning Officer


Cathy Leary


Planning Officer 


Helen Maclennan


Homeless Services 


Manager


Lorraine Graham


Private Sector Housing 


Manager


Andrew White


Housing Strategy & 


Development Officer


Isobel MacKenzie


Admin Assistant


Murdina MacKenzie


Housing Strategy 


Assistant


Kathleen Harper


Homeless Persons Asst


Margaret MacPhail


Homeless Support 


Officer


Edna Morrison


Accommodation Warden


Heather Murray


Accommodation Warden


Finlay MacSween


Accommodation Warden


Grant Hunter


Clerk/Typist PT


Catriona Macdonald


Development 


Management


Housing Services Building Standards


Planning 


Manager (Policy) 


(Balivanich)


Diane 


Macpherson


Building 


Standards 


Manager


John Gillies


Planning Technician


Kenny Maciver


Technician


Susan Rabe


THI Project Manager


Ian Wilson


Clerical Assistant


Marina Graham


Planning  Officer 


Eric Wojchik


Tenancy Support 


Worker (Balivanich)


Mary Steele


Service Team


Leaders


Planning Officer (PT) 


Mairi Mackinnon


Planning Enforcement 


Officer 


Iain Macleod


Head of Economic 


Development


Joe Macphee


Consumer & Environmental 


Services Manager


Colm Fraser


Consumer & Environmental 


Services Team


Economic Development Team


Strategy Team


Strategy Manager


John Cunningham


Countryside Access and 


Environment Officer


Paul Tyler (17.5 Hrs)




_1410269251.vsd

Name
Title



Name
Title




Building Standards




Building Standards Officer (Career Grade)
George Stewart



Senior
Building Standards Officer
Donald Thomson



 Building Standards Manager
John Gillies



Planning Technician

Kenny Maciver



Research Officer
Kathleen Shirkie



Biodiversity Officer
(Balivanich)
Anne Maclellan (17.5 Hrs)



Housing Services
Manager
Iain Watson



Building Standards Officer (Career Grade) 
Alasdair Maclean



Head of Economic Development
Joe Macphee



Service Team
 Leaders



Building Standards Assistant 
Mark Macleod



Building Standards Officer (Career Grade)
Ian MacRitchie



Building Standards Officer (Career Grade) (Balivanich)
John Macmillan



Building Standards Officer (Career Grade) (Balivanich)
Elizabeth Spark



Planning Officer (PT) 
Mairi Mackinnon



Technical Support Officer
Caitrina MacFarlane



Technician

Susan Rabe



Planning Manager (Development Management)
Morag Ferguson



Planning Enforcement Officer 
Iain Macleod



Director
Calum Iain MacIver



Planning Officer
 (Career Grade)
Isla MacArthur



Strategy Team



Planning Officer
(Career Grade)
Mairi Maciver



Strategy Manager
John Cunningham



Strategic Planning & Projects



Development Department Structure June 2012 



Homeless Services Manager
Lorraine Graham






